## Sheet1
WORK BREAK DOWN STRUCTURE
FOREST ECOLOGY AND GREEN COVER MONITORING SYSTEM
ASHWIN S
TASKS | START DATE | END DATE
Literature survey | 2019-09-20 | 2019-09-22
System requirement specification | 2019-09-24 | 2019-09-27
Recieved sensors required | 2019-09-30 | 2019-09-30
working on transferring and receiving data through web | 2019-10-02 | 2019-10-05
learning java script and json data accessing | 2019-10-08 | 2019-10-20
working on ui requirments | 2020-02-06 | 2020-02-07
learning web application development with dynamic data representation | 2020-02-08 | 2020-02-12
working on creating login page | 2020-02-15 | 2020-02-18
working on creating database | 2020-02-25 | 2020-03-01
working on creating main web page | 2020-02-03 | 2020-05-03
creating different components in a web page | 2020-03-03 | 2020-03-10
working on creating dynamic graph | 2020-03-12 | 2020-03-14
learning thingspeak | 2020-03-17 | 2020-03-22
working on live video output box on web page | 2020-03-24 | 2020-03-29
working on connecting web application and thingspeak | 2020-04-01 | 2020-04-03
Accessing different sensors data and creating threshold in visualization | 2020-04-05 | 2020-04-13
implementing graph visualization in web page | 2020-04-16 | 2020-04-17
working on creating dynamic alert display in the web page | 2020-04-20 | 2020-04-24
working on creating graph which displays data history | 2020-04-25 | 2020-04-27
working onintegration of different pages and data base | 2020-04-29 | 2020-04-30
fine tuning design and looks | 2020-05-01 | 2020-05-01
working on project report | 2020-02-05 | 2020-05-05