## Sheet1
WORK BREAK DOWN STRUCTURE
FOREST ECOLOGY AND GREEN COVER MONITORING SYSTEM
SOWMYA V S BHATT
TASKS | START DATE | END DATE
Literature survey | 2019-09-20 | 2019-09-22
knowing about python programing and image processing | 2019-09-24 | 2019-09-27
setting up the image processing environment | 2019-09-30 | 2019-09-30
Working on live streaming with webcam programatically | 31/09/2019 | 2019-10-01
Face detection | 2019-10-01 | 2019-10-01
Green color detection | 2019-10-02 | 2019-10-03
working on detecting multiple faces | 2019-10-04 | 2019-10-06
working on increasing and decreasing frame rate | 2019-10-08 | 2019-10-08
working on green pixel counting | 2019-10-10 | 2019-10-20
learning about object detection | 2020-02-06 | 2020-02-07
knowing about machine learning | 2020-02-08 | 2020-02-10
working on environmen setup of image processing | 2020-02-15 | 2020-02-18
learning about how to train a customized model | 2020-02-25 | 2020-03-01
how to create image dataset | 2020-02-03 | 2020-05-03
understanding caffe model | 2020-06-03 | 2020-06-03
implementation of human detection using caffe model | 2020-08-03 | 2020-10-03
working with image downloader and label Img | 2020-03-12 | 2020-03-13
working on setting up of training environment | 2020-03-14 | 2020-03-17
craeting a image data set of 1000 images | 2020-03-18 | 2020-03-22
learning about online model training | 2020-03-24 | 2020-03-29
working on google colab | 2020-04-01 | 2020-04-03
starting the training of saw detection model | 2020-04-05 | 2020-04-13
testing the model with a random saw image data | 2020-04-15 | 2020-04-15
testing the model with image captured by raspberrypi | 2020-04-16 | 2020-04-17
Integrating object detcetion with green pixel count | 2020-04-18 | 2020-04-18
accessing live stream video from raspberypi | 2020-04-20 | 2020-04-24
accessing live stream video from raspberypi to object detection code programmaticaaly | 2020-04-25 | 2020-04-27
learning about thingspeak | 2020-04-29 | 2020-04-29
sending output data to thingspeak | 2020-04-30 | 2020-04-30
fine tuning object detection code to print represantable output which is later transformed to thingspeak | 2020-05-01 | 2020-05-01
working on project report | 2020-02-05 | 2020-05-05