## Sheet1
WORK BREAK DOWN STRUCTURE
FOREST ECOLOGY AND GREEN COVER MONITORING SYSTEM
SUDINA K R
TASKS | START DATE | END DATE
Literature survey | 2019-09-20 | 2019-09-22
System requirement specification | 2019-09-24 | 2019-09-25
Recieved sensors required | 2019-09-30 | 2019-09-30
Working on connection related videos and coding part | 09/31/2019 | 2019-10-01
Implemented Arduino connection | 2019-10-03 | 2019-10-03
Working on how to connect multiple sensors and putting it to thinkspeak | 2019-10-04 | 2019-10-06
connected hardware result to thingspeak | 2019-10-06 | 2019-10-06
Raspberry pi received | 2020-02-06 | 2020-02-06
Working on raspberry pi setup | 2020-02-07 | 2020-02-10
trying to connect sensors to raspberry pi instead of arduino | 2020-02-15 | 2020-02-20
sending data from Rpi to thingspeak | 2020-02-21 | 2020-02-22
interfacing raspberri pi to camera module | 2020-02-24 | 2020-02-24
implementing green detection via raspberry pi camera module | 2020-02-25 | 2020-02-28
implementation done | 2020-03-02 | 2020-03-02
review done | 2020-03-09 | 2020-03-09
Trying to implement flame detection using camera module | 2020-03-20 | 2020-03-22
implementing sensor part again in arduino | 2020-04-02 | 2020-04-05
sending data from arduino to thingspeak | 2020-04-06 | 2020-04-06
sending trial data from raspberry pi to thingspeak | 2020-04-08 | 2020-04-10
sending green pixel data from Rpi to thingspeak | 2020-04-11 | 2020-04-11
trying to imstall tensor flow in raspberry pi | 2020-04-12 | 2020-04-15
running saw detection code in Rpi | 2020-04-16 | 2020-04-17
saw alert shown in thingspeak | 2020-04-19 | 2020-04-19
fine tuning | 2020-04-20 | 2020-04-25
lora transiever received | 2020-04-26 | 2020-04-26
working on lora connection with arduino | 2020-04-27 | 2020-04-28
sending data from arduino to thingspeak via lora | 2020-04-30 | 2020-04-30
testing the device in near by park | 2020-05-02 | 2020-05-02
working on project report and ppt | 2020-05-03 | 2020-05-05